## Welcome
BMC AMIGO TSCO Upgrade Guide
Thank you for choosing to use the BMC AMIGO program to upgrade from your current version to supported TSCO version.
This guide will provide step by step instructions to help you to create your customized install plan.
READ ME FIRST
Please ensure you take the following essential considerations in mind before upgrading:
1) Upgrading has a limit of 2 versions. If you are on TSCO 10.5 or lower, please upgrade first to TSCO 10.7.01/11.0/11.3,11.5 before proceeding
2) Remedy SSO (RSSO) & the TrueSight Presentation Server TSPS need to be installed on their own servers/VMs prior to install or Upgrade of TSCO.
3) Remedy SSO (RSSO) replaces Atrium SSO (ASSO) as a supported Single Sign On platform.
4) If migrating from 10.7, it is recommended first to upgrade to 10.7.01 in most cases to preserve custom view formats.
5) Custom views from earlier versions must be migrated prior to upgrade or they will be lost.
6) Note: RSSO is creates a self-signed certificate which is only valid for 90 days. (A change from Atrium SSO which is valid for 10 years).
When ready to start your AMIGO upgrade, please click below as per TSCO version upgrade
Starter
10.7.0
11.0.0
11.3.01
11.5.01
20.02

## 10.7
AMIGO: Starter
| Tasks | Comments | Link | Task Status | Task Owner
Step | Prechecks and Tasks before Upgrade
1 | Begin Sizing | Provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment. (Providing these documents right away will greatly speed up your AMIGO upgrade review). | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000152366
2 | Review Release Notes, Notices, and Enhancements | This section provides information about what is new or changed in this space, including urgent issues, documentation updates, service packs, and patches. | https://docs.bmc.com/docs/display/btco107/Release+notes+and+notices
3 | Review Upgrade Path from 9.x to 10.x | You can perform a direct upgrade of the Application Server TSCO component by running the installation program from the wizard-based UI or in silent mode. When upgrading from a version of the product prior to the last two releases you must perform at least one interim upgrade before you can perform a direct upgrade. | https://docs.bmc.com/docs/display/btco107/Supported+upgrade+paths
4 | Supported resources or OS requirements check for TSCO and Databse servers | Before Upgrading the TrueSight Capacity Optimization product, ensure that the target systems meet the following software requirements: | https://docs.bmc.com/docs/display/btco107/System+requirements
5 | Verfy if migration of the Application Server is required | Migration of Application Server and its components from one server to another server is required in any one of the following scenarios: 1) Support for currently installed version of operating system/DB is stopped. 2) Upgrade to recent/different version of an operating system/DB is required in your environment. | https://docs.bmc.com/docs/display/btco107/Migrating+the+Application+Server+components+to+another+server
6 | Backup Strategies before Upgrade | Before you begin the upgrade, ensure that you have a valid TSCO database backup. If not, perform a full database and installation directory file-system level backup for all TrueSight Capacity Optimization servers i.e. AS, EE and REE (create a tar archive or take a snapshot of TrueSight Capacity Optimization VMs). Note: If you are using a local repository, and want to use a shared repository after upgrade,Take a backup of your existing repository folder. | https://docs.bmc.com/docs/display/btco107/Preparing+to+upgrade+the+Application+Server
7 | Applying latest CHF's to TSCO server's | Please ensure Application and ETL Engine server are patched to most current CHF of existing version,use below KA to check for latest CHF's for TSCO: | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000097159
8 | Installing Atrium SSO | If you are upgrading from version 10.0 or earlier, You need to install Atrium Single Sign-On before proceeding with the Application Server upgrade | https://docs.bmc.com/docs/display/sso90/Installing+BMC+Atrium+Single+Sign-On+in+different+environments
9 | Installing Presentation Server | If you are upgrading from version 10.0 or earlier, or if you did not install the TrueSight Presentation Server with version 10.3, you must install it before proceeding with the Application Server upgrade. | https://docs.bmc.com/docs/display/btco107/Installing+the+Presentation+Server
10 | Request for Information Questionnaire | The Questionnaire on the next sheet is a guide to help you inventory your current environment while considering potential growth. If you are expecting significant growth from your current environment or if you are using features that may be deprecated in the newer version, please read and send the questionnaire to TSCO Support for additional guidance. (Recommended). | Questionnaire

## 11.0
AMIGO: Starter
| Tasks | Comments | Link | Task Status | Task Owner
Step | Prechecks and Tasks before Upgrade
1 | Begin Sizing | Provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment. (Providing these documents right away will greatly speed up your AMIGO upgrade review). | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000152366
2 | Review Release Notes, Notices, and Enhancements | This section provides information about what is new or changed in this space, including urgent issues, documentation updates, service packs, and patches. | https://docs.bmc.com/docs/display/btco110/Release+notes+and+notices
3 | Review Upgrade Path from 9.x to 11.x | You can perform a direct upgrade of the Application Server TSCO component by running the installation program from the wizard-based UI or in silent mode. When upgrading from a version of the product prior to the last two releases you must perform at least one interim upgrade before you can perform a direct upgrade. | https://docs.bmc.com/docs/display/btco110/Supported+upgrade+paths
4 | Supported resources or OS requirements check for TSCO and Databse servers | Before Upgrading the TrueSight Capacity Optimization product, ensure that the target systems meet the following software requirements: | https://docs.bmc.com/docs/display/btco110/System+requirements
5 | Verfy if migration of the Application Server is required | Migration of Application Server and its components from one server to another server is required in any one of the following scenarios: 1) Support for currently installed version of operating system/DB is stopped. 2) Upgrade to recent/different version of an operating system/DB is required in your environment. | https://docs.bmc.com/docs/display/btco110/Migrating+the+Application+Server+components+to+another+server
6 | Backup Strategies before Upgrade | Before you begin the upgrade, ensure that you have a valid TSCO database backup. If not, perform a full database and installation directory file-system level backup for all TrueSight Capacity Optimization servers i.e. AS, EE and REE (create a tar archive or take a snapshot of TrueSight Capacity Optimization VMs). Note: If you are using a local repository, and want to use a shared repository after upgrade,Take a backup of your existing repository folder. | https://docs.bmc.com/docs/display/btco110/Preparing+to+upgrade+the+Application+Server
7 | Applying latest CHF's to TSCO server's | Please ensure Application and ETL Engine server are patched to most current CHF of existing version,use below KA to check for latest CHF's for TSCO: | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000097159
8 | Installing Remedy SSO | The TrueSight family of products use Remedy Single Sign-On (or Remedy SSO) to authenticate and manage users and user groups for all integrated TrueSight components. (This is a requirement for installation of TSCO 11.x). | https://docs.bmc.com/docs/display/btco110/Preparing+to+install+Remedy+Single+Sign-On
9 | Migrating from Atrium SSO to Remedy SSO (TSCO 10.x only) | Migrating from Atrium SSO to Remedy Single Sign-On is required for authentication. After you upgrade,we would recommend you to run the utility from below link to import internal user data from Atrium SSO and then exporting the same to newly installed Remedy SSO. | https://docs.bmc.com/docs/display/btco110/Migrating+to+Remedy+SSO
10 | Upgrading Presentation Server | You can upgrade the TrueSight Presentation Server by running the installation program from a wizard or from a command line. Refer to the topics from below link to prepare before upgrade: | https://docs.bmc.com/docs/display/btco110/Performing+the+Presentation+Server+upgrade
11 | Recreating Views | Custom views created in the TSCO 10.x standalone console will not be available after upgrading to TSCO 11.0. To continue using these custom views, you must first create them in the TrueSight Console (TSPS) before you upgrade to version 11.0. In TrueSight Capacity Optimization version 11.0, all OOTB views have been migrated to the TrueSight Console (TSPS). | https://docs.bmc.com/docs/display/btco110/Re-creating+custom+views
12 | Converting TSCO views to TSPS format views | Before the upgrade to 11.0, if you have any custom views in TSCO 10.x, you need to migrate the views to TSPS using the utility from the communities’ link or they may be lost. To use the utility for migration of views, you need to be on 10.7.01 version for TSCO. The link will provide the steps and migration utility tool. | https://communities.bmc.com/community/bmcdn/capacity_management/blog/2017/10/18/view-migration-toolkit-for-truesight-capacity-optimization
13 | Request for Information Questionnaire | The Questionnaire on the next sheet is a guide to help you inventory your current environment while considering potential growth. If you are expecting significant growth from your current environment or if you are using features that may be deprecated in the newer version, please read and send the questionnaire to TSCO Support for additional guidance. (Recommended). | Questionnaire

## 11.3.01
AMIGO: Starter
| Tasks | Comments | Link | Task Status | Task Owner
Step | Prechecks and Tasks before Upgrade
1 | Begin Sizing | Provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment. (Providing these documents right away will greatly speed up your AMIGO upgrade review). | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000152366
2 | Review Release Notes, Notices, and Enhancements | This section provides information about what is new or changed in this space, including urgent issues, documentation updates, service packs, and patches. | https://docs.bmc.com/docs/display/btco113/Release+notes+and+notices
3 | Review Upgrade Path from 9.x to 11.x | You can perform a direct upgrade of the Application Server TSCO component by running the installation program from the wizard-based UI or in silent mode. When upgrading from a version of the product prior to the last two releases you must perform at least one interim upgrade before you can perform a direct upgrade. If you have custom view in 9.X or later then it is mendatory to upgrade to 10.7.01 and install ASSO. If no custom viewes then you can upgrade to 10.7.01 without ASSO and from 10.7.01 upgrade to 11.X with RSSO | https://docs.bmc.com/docs/display/btco113/Supported+upgrade+paths
4 | Supported resources or OS requirements check for TSCO and Databse servers | Before Upgrading the TrueSight Capacity Optimization product, ensure that the target systems meet the following software requirements: | https://docs.bmc.com/docs/display/btco113/System+requirements
5 | Verify if migration of the Application Server is required | Migration of Application Server and its components from one server to another server is required in any one of the following scenarios: 1) Support for currently installed version of operating system/DB is stopped. 2) Upgrade to recent/different version of an operating system/DB is required in your environment. | https://docs.bmc.com/docs/display/btco113/Migrating+the+Application+Server+components+to+another+server
6 | Backup Strategies before Upgrade | Before you begin the upgrade, ensure that you have a valid TSCO database backup. If not, perform a full database and installation directory file-system level backup for all TrueSight Capacity Optimization servers i.e. AS, EE and REE (create a tar archive or take a snapshot of TrueSight Capacity Optimization VMs). Note: If you are using a local repository, and want to use a shared repository after upgrade,Take a backup of your existing repository folder. | https://docs.bmc.com/docs/display/btco113/Preparing+to+upgrade+the+Application+Server
7 | Applying latest CHF's to TSCO server's | Please ensure Application and ETL Engine server are patched to most current CHF of existing version,use below KA to check for latest CHF's for TSCO: | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000097159
8 | Installing Remedy SSO | The TrueSight family of products use Remedy Single Sign-On (or Remedy SSO) to authenticate and manage users and user groups for all integrated TrueSight components. (This is a requirement for installation of TSCO 11.x). | https://docs.bmc.com/docs/display/btco113/Installing+Remedy+Single+Sign-On
9 | Migrating from Atrium SSO to Remedy SSO (TSCO 10.x only) | Migrating from Atrium SSO to Remedy Single Sign-On is required for authentication. After you upgrade,we would recommend you to run the utility from below link to import internal user data from Atrium SSO and then exporting the same to newly installed Remedy SSO. For setting up AtriumSSO to connect to the LDAP refer : https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000139411 | https://docs.bmc.com/docs/display/btco113/Migrating+to+Remedy+SSO
10 | Upgrading Presentation Server | You can upgrade the TrueSight Presentation Server by running the installation program from a wizard or from a command line. Refer to the topics from below link to prepare before upgrade: | https://docs.bmc.com/docs/display/btco113/Performing+the+Presentation+Server+upgrade
11 | Recreating Views | Custom views created in the TSCO 10.x standalone console will not be available after upgrading to TSCO 11.3.01. To continue using these custom views, you must first create them in the TrueSight Console (TSPS) before you upgrade to version 11.3.01. In TrueSight Capacity Optimization version 11.3.01, all OOTB views have been migrated to the TrueSight Console (TSPS). | https://docs.bmc.com/docs/display/btco113/Re-creating+custom+views
12 | Converting TSCO views to TSPS format views | Before the upgrade to 11.3.01, if you have any custom views in TSCO 10.x, you need to migrate the views to TSPS using the utility from the communities’ link or they may be lost. To use the utility for migration of views, you need to be on 10.7.01 version for TSCO. The link will provide the steps and migration utility tool. | https://communities.bmc.com/community/bmcdn/capacity_management/blog/2017/10/18/view-migration-toolkit-for-truesight-capacity-optimization
13 | Request for Information Questionnaire | The Questionnaire on the next sheet is a guide to help you inventory your current environment while considering potential growth. If you are expecting significant growth from your current environment or if you are using features that may be deprecated in the newer version, please read and send the questionnaire to TSCO Support for additional guidance. (Recommended). | Questionnaire
14 | Check Aging Class Mapping | Before upgrade to 11.3.01 make a note of Aging Class Mapping. Because post upgrade it is possible that Standard is moved from MEDIUM to LONG retention, as you can see from the red mark in screenshot. The default mapping for Standard is MEDIUM

## 11.5.01
AMIGO: Starter
| Tasks | Comments | Link | Task Status | Task Owner
Step | Prechecks and Tasks before Upgrade
1 | Begin Sizing | Provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment. (Providing these documents right away will greatly speed up your AMIGO upgrade review). | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000152366
2 | Review Release Notes, Notices, and Enhancements | This section provides information about what is new or changed in this space, including urgent issues, documentation updates, service packs, and patches. | https://docs.bmc.com/docs/display/btco115/Release+notes+and+notices
3 | Review Upgrade Path from 9.x to 11.x | You can perform a direct upgrade of the Application Server TSCO component by running the installation program from the wizard-based UI or in silent mode. When upgrading from a version of the product prior to the last two releases you must perform at least one interim upgrade before you can perform a direct upgrade. If you have custom view in 9.X or later then it is mendatory to upgrade to 10.7.01 and install ASSO. If no custom viewes then you can upgrade to 10.7.01 without ASSO and from 10.7.01 upgrade to 11.X with RSSO | https://docs.bmc.com/docs/display/btco115/Supported+upgrade+paths
4 | Supported resources or OS requirements check for TSCO and Databse servers | Before Upgrading the TrueSight Capacity Optimization product, ensure that the target systems meet the following software requirements: | https://docs.bmc.com/docs/display/btco115/Planning
5 | Backup Strategies before Upgrade | Before you begin the upgrade, ensure that you have a valid TSCO database backup. If not, perform a full database and installation directory file-system level backup for all TrueSight Capacity Optimization servers i.e. AS, EE and REE (create a tar archive or take a snapshot of TrueSight Capacity Optimization VMs). Note: If you are using a local repository, and want to use a shared repository after upgrade,Take a backup of your existing repository folder. | https://docs.bmc.com/docs/display/btco115/Preparing+to+upgrade+TrueSight+Capacity+Optimization
7 | Applying latest CHF's to TSCO server's | Please ensure Application and ETL Engine server are patched to most current CHF of existing version,use below KA to check for latest CHF's for TSCO: | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000097159
8 | Installing Remedy SSO | The TrueSight family of products use Remedy Single Sign-On (or Remedy SSO) to authenticate and manage users and user groups for all integrated TrueSight components. (This is a requirement for installation of TSCO 11.x). | https://docs.bmc.com/docs/display/btco115/Installing#Installing-rsso
9 | Migrating from Atrium SSO to Remedy SSO (TSCO 10.x only) | Migrating from Atrium SSO to Remedy Single Sign-On is required for authentication. After you upgrade,we would recommend you to run the utility from below link to import internal user data from Atrium SSO and then exporting the same to newly installed Remedy SSO. For setting up AtriumSSO to connect to the LDAP refer : https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000139411 | https://docs.bmc.com/docs/display/btco115/Migrating+to+Remedy+SSO
10 | Upgrading Presentation Server | You can upgrade the TrueSight Presentation Server by running the installation program from a wizard or from a command line. Refer to the topics from below link to prepare before upgrade: | https://docs.bmc.com/docs/display/btco115/Preparing+to+upgrade+the+Presentation+Server
11 | Recreating Views | Custom views created in the TSCO 10.x standalone console will not be available after upgrading to TSCO 11.5.01. To continue using these custom views, you must first create them in the TrueSight Console (TSPS) before you upgrade to version 11.5.01. In TrueSight Capacity Optimization version 11.5.01, all OOTB views have been migrated to the TrueSight Console (TSPS). | https://docs.bmc.com/docs/display/tempco/Re-creating+custom+views
12 | Converting TSCO views to TSPS format views | Before the upgrade to 11.5.01, if you have any custom views in TSCO 10.x, you need to migrate the views to TSPS using the utility from the communities’ link or they may be lost. To use the utility for migration of views, you need to be on 10.7.01 version for TSCO. The link will provide the steps and migration utility tool. | https://communities.bmc.com/community/bmcdn/capacity_management/blog/2017/10/18/view-migration-toolkit-for-truesight-capacity-optimization
13 | Request for Information Questionnaire | The Questionnaire on the next sheet is a guide to help you inventory your current environment while considering potential growth. If you are expecting significant growth from your current environment or if you are using features that may be deprecated in the newer version, please read and send the questionnaire to TSCO Support for additional guidance. (Recommended). | Questionnaire
14 | Check Aging Class Mapping | Before upgrade to 11.5.01 make a note of Aging Class Mapping. Because post upgrade it is possible that Standard is moved from MEDIUM to LONG retention, as you can see from the red mark in screenshot. The default mapping for Standard is MEDIUM

## 20.02
AMIGO: Starter
| Tasks | Comments | Link | Task Status | Task Owner
Step | Prechecks and Tasks before Upgrade
1 | Begin Sizing | Provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment. (Providing these documents right away will greatly speed up your AMIGO upgrade review). | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000152366
2 | Review Release Notes, Notices, and Enhancements | This section provides information about what is new or changed in this space, including urgent issues, documentation updates, service packs, and patches. | https://docs.bmc.com/docs/display/btco2002/Release+notes+and+notices
3 | Review Upgrade Path from 9.x to 11.x to 20.02 | You can perform a direct upgrade of the Application Server TSCO component by running the installation program from the wizard-based UI or in silent mode. When upgrading from a version of the product prior to the last two releases you must perform at least one interim upgrade before you can perform a direct upgrade. If you have custom view in 9.X or later then it is mendatory to upgrade to 10.7.01 and install ASSO. If no custom viewes then you can upgrade to 10.7.01 without ASSO and from 10.7.01 upgrade to 11.X with RSSO | https://docs.bmc.com/docs/display/btco2002/Supported+upgrade+paths
4 | Supported resources or OS requirements check for TSCO and Databse servers | Before Upgrading the TrueSight Capacity Optimization product, ensure that the target systems meet the following software requirements: | https://docs.bmc.com/docs/display/btco2002/Planning
5 | Backup Strategies before Upgrade | Before you begin the upgrade, ensure that you have a valid TSCO database backup. If not, perform a full database and installation directory file-system level backup for all TrueSight Capacity Optimization servers i.e. AS, EE and REE (create a tar archive or take a snapshot of TrueSight Capacity Optimization VMs). Note: If you are using a local repository, and want to use a shared repository after upgrade,Take a backup of your existing repository folder. | https://docs.bmc.com/docs/display/btco2002/Preparing+to+upgrade+TrueSight+Capacity+Optimization
7 | Applying latest CHF's to TSCO server's | Please ensure Application and ETL Engine server are patched to most current CHF of existing version,use below KA to check for latest CHF's for TSCO: | https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000097159
8 | Installing Remedy SSO | The TrueSight family of products use Remedy Single Sign-On (or Remedy SSO) to authenticate and manage users and user groups for all integrated TrueSight components. (This is a requirement for installation of TSCO 11.x). | https://docs.bmc.com/docs/display/btco2002/Installing#Installing-rsso
9 | Migrating from Atrium SSO to Remedy SSO (TSCO 10.x only) | Migrating from Atrium SSO to Remedy Single Sign-On is required for authentication. After you upgrade,we would recommend you to run the utility from below link to import internal user data from Atrium SSO and then exporting the same to newly installed Remedy SSO. For setting up AtriumSSO to connect to the LDAP refer : https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000139411 | https://docs.bmc.com/docs/display/btco2002/migrating+to+remedy+sso
10 | Upgrading Presentation Server | You can upgrade the TrueSight Presentation Server by running the installation program from a wizard or from a command line. Refer to the topics from below link to prepare before upgrade: | https://docs.bmc.com/docs/display/btco2002/Preparing+to+upgrade+the+Presentation+Server
11 | Recreating Views | Custom views created in the TSCO 10.x standalone console will not be available after upgrading to TSCO 20.02. To continue using these custom views, you must first create them in the TrueSight Console (TSPS) before you upgrade to version 20.02 In TrueSight Capacity Optimization version 20.02, all OOTB views have been migrated to the TrueSight Console (TSPS). | https://docs.bmc.com/docs/display/btco2002/adding+a+custom+view
12 | Converting TSCO views to TSPS format views | Before the upgrade to 20.02, if you have any custom views in TSCO 10.x, you need to migrate the views to TSPS using the utility from the communities’ link or they may be lost. To use the utility for migration of views, you need to be on 10.7.01 version for TSCO. The link will provide the steps and migration utility tool. | https://communities.bmc.com/community/bmcdn/capacity_management/blog/2017/10/18/view-migration-toolkit-for-truesight-capacity-optimization
13 | Request for Information Questionnaire | The Questionnaire on the next sheet is a guide to help you inventory your current environment while considering potential growth. If you are expecting significant growth from your current environment or if you are using features that may be deprecated in the newer version, please read and send the questionnaire to TSCO Support for additional guidance. (Recommended). | Questionnaire
14 | Check Aging Class Mapping | Before upgrade to 20.02 make a note of Aging Class Mapping. Because post upgrade it is possible that Standard is moved from MEDIUM to LONG retention, as you can see from the red mark in screenshot. The default mapping for Standard is MEDIUM

## Questionnaire
Question | RFI Checklist | Questions?
1 | TSCO General Details | What is the current OS version on TSCO servers (App. servers, ETL Engines)?
What is your current Database Version (server)?
What is your current Oracle client version (on the Application servers and ETL Engines)?
Have you installed any Market Zone (partner provided, e.g Moviri or Sentry) additional packages? (Check : "Administration > System > Maintenance > Additional Packages" or "Administration > System > Maintenance > Patches")
2 | Current Architecture | What is your current deployment architecture like?Archirtecture diagram or previous Sizing provided?
How many Applications Servers are you running in your environment?
What is running on each application server (web,datahub)?
How many ETL Engines?
How many Remote ETL Engines?
Do you have Oracle RAC (A multi-instance Oracle environment with load balancing or fail-over support)?
Hardware information of the servers (Total Memory, Number of CPUs, Disk I/- sub-system TSCO configuration for the Capacity Optimization aka TSCO database)
3 | Users | How many Users are associated with the current environment? (how many users in your environment,interact with the TSCO web UI on a regular basis?)
4 | Dataflow Details | How many entities are associated with this environment? [Create a report for the domain: Workspace -> All Domains -> Add Works -> Add Report -> Template* - Diagnostic, Managed Entity]
What is your current data flow (Data Flow diagnostic report)?
Are you using out of the box ETL? How many of them are in use?
5 | Types of Customization | Do you have any custom ETLs?
Are the custom ETL's being developed and deployed using Integration Studio?
Are the custom ETL's using Public Views (PVs) or the TSCO internal database schema tables?
Are you using any “auto ETL”?
Are they using Public Views (PVs) or are they using the TSCO internal database schema tables?
Do you have any custom report templates?
Are they using Public Views (PVs) or are they using TSCO internal database schema tables?
Do you have any custom SQL Data Mart?
Are they using Public Views (PVs) or are they using TSCO internal database schema tables?
Do you have any custom views?
Are they using Public Views (PVs) or are they using TSCO internal database schema tables?
6 | Gateway Server [BPA console] details | What is your Gateway Server version?
What is the Service Pack which is installed on it?
What is the Operating System Version?
How many Gateway Server you are using?
How many manager runs are associated with each TSCO console?
Are you using a 24 hour data TSCO collection?
Are you using Investigate?
Are you using General Manager to manage multiple TSCO consoles?
Are you using agentless data TSCO collection?
Are you using mpopulate or automator?
What is the TSCO configuration of machine on which Database Server is installed (RAM, CPU, File System size)?
7 | Agent [Perform or BPA Agent] details | How many agents are associated with the TSCO console? (isn't this the same question as "How many nodes are associated with each TSCO console?")
What version(s) are your Agents?
Are you using vcenter Proxy?
Are you using windows Proxy?
8 | BMC Perceiver details | What is your current Perceiver Version?
What is the Operating System Version?
Are you using General Manager option on Perceiver?
Are you using Virtualization Planning?
How many Data sources are attached to the Perceiver?
Have you customized views on Perceiver?
How many users have access to Perciever?
9 | Important Note | Also, capture and provide the TSCO Sizing Report and Dataflow Diagnostics Report. These reports are useful for getting a picture of the current load and health of the environment.
For TrueSight Capacity Optimization, how do I create the 'Sizing Report'? Note:Sizing report needs to be in xlsx format.
For TSCO, how do I capture the 'Diagnostic Report - Data Flow and Statistics' report?