## Upgrade Checklist
" Welcome to the AMIGO upgrade program. This spreadsheet contains: * the Control-M Upgrade Checklist For 9.0.18 & 9.0.19 & 9.0.20: * EM sample MIGRATION plan (source version lower than 9.0) and EM sample UPGRADE plan (in place upgrade for EM 9.0, video: https://youtu.be/KIY2UgX1PkI) * Server sample MIGRATION plan (source version lower than 9.0) and Server sample UPGRADE plan (in place upgrade for Control-M/Server 9.0, video: https://youtu.be/vHU8rWFMQBg) * Ensure that all of your existing Control-M Reporting Facility reports and data are migrated and converted into Control-M Reports, as described in video: https://youtu.be/gnWfoDlnk7U For 9.0.00: * EM sample UPGRADE plan and Server sample UPGRADE plan. Video: https://youtu.be/2YsMucXKpcM) **AMIGO program only covers the upgrade between supported versions. If currently on an unsupported version, it will be necessary to review the Migration Guide for options to get to the latest supported version. Open a regular Support case at www.bmc.com/support for specific technical questions.** Please fill out the "Control-M Upgrade Checklist", review the other information provided and then send this spreadsheet back to BMC Support using your AMIGO Starter issue. BMC Support will contact you to discuss your upgrade plan.
Control-M Upgrade Checklist
1. What products are being upgraded? If you are currently using an out of support version, please contact your BMC Account Manager rep for assistance.
| From |  |  |  | To
| Control-M Version & Fixpack level | Operating System & version | Database type & version | Hostname | Control-M Version & Fixpack level | Operating System & version | Database type & version | Hostname
Enterprise Manager
Control-M/Server
(add lines for other servers)
If you're using MSSQL server, please install MSSQL client 2012.
2. Why are you upgrading?
3. What benefits do you hope to gain with the upgrade? Click the next link to learn more about Control-M 9.0 features: | [5 empty] | Maximizing Control-M 9.0 investment
4. Is this your first Control-M upgrade or are you familiar with the Control-M upgrade process?
5. If you want to validate that your hardware meets the requirements for Control-M, please submit a sizing ticket.
6. Review the Control-M Workload Automation Guide:
For V8: | http://documents.bmc.com/supportu/952/50/57/485057/485057.pdf
For V9: | http://documents.bmc.com/supportu/952/12/94/491294/491294.pdf
For V9.0.18: | UPGRADE (in place upgrade for 9.0 components) |  |  | http://documents.bmc.com/supportu/9.0.18/help/Main_help/en-US/index.htm#5085.htm
| MIGRATE (source version lower than 9.0) |  |  | http://documents.bmc.com/supportu/9.0.18/help/Main_help/en-US/index.htm#4638.htm
For 9.0.19: | UPGRADE (in place upgrade for 9.0.x components) |  |  | http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#5085.htm
For 9.0.20: | UPGRADE (in place upgrade for 9.0.x components) |  |  | http://documents.bmc.com/supportu/9.0.20/help/Main_help/en-US/index.htm#5085.htm
7. Check OS and DB compatibility using the BMC compatability tool: |  |  |  | https://customerapps.bmc.com/spac/o/welcome.html
8. Review the EM sample plan according to the version that you are upgrading.
9. Review the Server sample plan according to the version that you are upgrading.
10. Review our videos:
For V8: | https://youtu.be/dyh4NPFFMtc
For V9: | https://youtu.be/2YsMucXKpcM
For V9.0.18: | https://youtu.be/vHU8rWFMQBg
https://youtu.be/KIY2UgX1PkI
https://youtu.be/gnWfoDlnk7U

## EM 9.0.18-9.0.19 migration plan
Enterprise Manager 9.0.18/9.0.19 Sample Migration Plan
New Software Installation | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts.
http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#4923.htm
Validate that the new server has the same time configuration than the source server
Install EM 9.0.18/9.0.19 and the latest EM fixpack
Activate EM add-ons (BIM, Forecast, Self Service, Workload Change Manager, etc)
Install the EM 9.0.18/9.0.19 client and latest fixpack
Install the EM 9.0.18/9.0.19 Migration Export Pack in the "old" EM environment
Testing | Start | Finish
On the "old" Control-M/Enterprise Manager database run the query below. If it throw results, you have duplicated folders in the EM database that could represent an issue for the upgrade, contact BMC Support to delete the duplicated entries. select DATA_CENTER, SCHED_TABLE, DSN, TABLE_STATUS, TBL_DELETION_TIMESTAMP, count(*) from DEF_VER_TABLES group by DATA_CENTER, SCHED_TABLE, DSN, TABLE_STATUS, TBL_DELETION_TIMESTAMP having count(*)>1;
On the "old" environment, run the Upgrade Export “Validation” report until there are no errors.
On the "old" environment, perform the steps described in the "Control-M Reporting Facility migration" section of the Migration guide to migrate reports from the old Control-M Reporting Facility to the new Control-M Reports. The next video describes the procedure:
https://youtu.be/gnWfoDlnk7U
http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#94108.htm
Export the "old" environment. You do not have to shutdown EM to perform this export.
Copy the export file to the new environment
Import the data into the new EM
Review the functionality of the EM 9.0.18/9.0.19 Workload Automation client. Review the Release Notes
Validate the functionality of the new EM client and Server
Test the Client Distribution tool
Import your reports into the new EM and test the Control-M reports job execution
Create a checklist of actions to verify the new installation after import(change a job, hold/free a job, re-run, view sysout, …)
Finalize upgrade details | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new EM 9.0.18/9.0.19 components are not running(gateway, GUI Server, GCS, CMS, CORBA naming service)
Verfiy new EM 9.0.18/9.0.19 database is running
EM cutover | Start | Finish
Verify all scheduling tables are in sync between EM and Control-M/Server.
Using CCM, shutdown the EM components in the old environment: GCS, GUI Server, GAS, gateways and any other EM components.
Shutdown the EM Configuration Agent, EM Configuration Management Server and the Naming Service.
Make sure the EM database is up.
Run the Upgrade Export utility to export the old environment
Copy the file created by the upgrade export to the new EM 9.0.18/9.0.19
Using CCM, shutdown the EM components in the new environment: GCS, GUI Server, GAS, gateways and any other EM components. If you are using Control-M/Enterprise Manager 9.0.18/9.0.19 with High Availability, please follow the next steps before performing the import: 1. Stop the Control-M/Enterprise Manager Configuration Agent on the secondary node. 2. Using CCM, shutdown the EM components in the primary server: GCS, GUI Server, GAS, gateways and any other EM components, stop the Control-M/Enterprise Manager Configuration Agent.
Run Upgrade Toolkit Import utility to import data into the new EM 9.0.18/9.0.19
Using the “root_menu” in Unix go to Activation Menu > Start all, On Windows go to services.msc in Windows, start the Control-M/Enterprise Manager configuration agent. If you are using Control-M/Enterprise Manager 9.0 .18 with High Availability, on the secondary EM, start the Control-M/Enterprise Manager Configuration Agent using "root_menu" for Unix and services.msc for Windows.
If the Control-M/Server is also being upgraded, perform "Elevate" for each Control-M/Server being upgraded before bringing up the gateway. During Elevate: Change the Host name from the OLD host to the NEW host name. If the elevate option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Using CCM, connect to CMS and verify the hostname, ports and definitions for the new environment.
Verify the new environment | Start | Finish
Verify components and gateways are running
Start EM GUI client, verify jobs.
Order new test table/jobs
View job definitions in the EM GUI
Verify different viewpoints
Verify all resources have been refreshed and new ones are being added/deleted properly
Access sysout and log files for a job
Perform normal AJF actions: hold, update, free, …
Verify security: view or add a user
Post Upgrade tasks | Start | Finish
Backup the new EM environment
Upgrade Complete

## Server 9.0.18-19 migration plan
Control-M/Server 9.0.18/9.0.19 Sample Migration Plan
New Software Installation | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts.
http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#4923.htm
Validate that the new server has the same time configuration and Control-M log retention than the source server
Install Control-M/Server 9.0.18/9.0.19 and the latest fixpack
Install the Control-M/Server 9.0.18/9.0.19 Migration Export Pack in the "old" server environment
Testing | Start | Finish
On the "old" environment, run the Control-M/Server Migration Export Pack “Validation” report until there are no errors.
Export the "old" environment. You do not have to shutdown the Control-M/Server to perform this export.
Copy the export file to the new environment
Import the data into the new Control-M/Server 9.0.18/9.0.19
Review the functionality of the Control-M/Server 9.0.18/9.0.19 Release Notes
Validate the functionality of the new Control-M/Server 9.0.18/9.0.19
Test the agent deployment utility
Review the config.dat from the old environment and add any customization to the new environment
If database is Oracle, ensure the config.dat "LANGUAGE_TYPE" setting is set correctly as the Control-M/Server database owner system variable NLS_LANG
Validate the SMTP server setting
Create a checklist of actions to verify the new installation after import(send a shout, send an email, …)
Copy customized scripts from the old to new environment
Finalize upgrade details | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new Control-M/Server 9.0.18/9.0.19 database is running
On the CCM stop the gateway of the Control-M/Server that will be upgraded and set it to unmanaged.
| Start | Finish
Control-M/Server cutover
Shutdown the old Control-M/Server configuration agent and Control-M/Server. Leave the database up and running. If you are using the migration export pack's functionality to add the new Control-M/Server 9.0.18/9.0.19 host name to the agents, you need to keep the old Control-M/Server up for the first part of the export and shut it down once the new host name has been added to complete the export of the active environment.
Run the migration export pack to export the old environment
Copy the file created by the upgrade export to the new Control-M/Server 9.0.18/9.0.19
Run Migration Export Pack's Import utility to import data into the new Control-M/Server 9.0.18/9.0.19. If you have Control-M/Server 9.0.18/9.0.19 with High Availability and Postgres, please follow the next steps before performing the import: 1. Change the replication mode to asynchronous on the primary (active) Control-M/Server: ctmha -ACTION UPDATE_REPLICATION_MODE ASYNC 2. Stop the Control-M/Server Configuration Agent on the secondary node. 3. Stop the Control-M/Server Configuration Agent and Control-M/Server on the primary node.
If you are upgrading from Control-M/Server 9.0.00 with Postgres database and high availability to Control-M/Server 9.0.19, please perform the next steps: 1. Do a backup copy of config.dat located in $HOME/ctm_server/data in both Control-M/Servers. 2. Edit the Control-M/Server file config.dat located in $HOME/ctm_server/data in both Control-M/Servers. 3. Modify the parameter PRIMARY_HOST_ID with the new environment details. 4. Modify the parameter SECONDARY_HOST_ID with the new environment details. 5. Save the file in both Control-M/Servers
Run ‘ctmdbcount’ on the source and target environment, compare both outputs to validate that all the tables have been imported.
Run 'ctmdbopt' to improve database performance
Validate that all the historical and statistics have been imported successfully.
Check Control-M/Server default protocol_version and server to agent port
Before starting the Control-M/Server 9.0.18/9.0.19, from the CCM, right-click this Control-M/Server and run Elevate datacenter. If the elevate option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Start the Control-M/Server and Control-M/Server configuration agent. If you have Control-M/Server 9.0.18/9.0.19 with High Availability and Postgres, please follow the next steps: 1. Start the Control-M/Server Configuration Agent and Control-M/Server on the primary node. 2. Start the Control-M/Server Configuration Agent on the secondary node. 3. On the Control-M Configuration Manager validate that High Availability is working correctly. 4. Change the replication mode back to synchronous by running the next command on the primary (active) Control-M/Server: ctmha -ACTION UPDATE_REPLICATION_MODE SYNC
| Start | Finish
Verify the new environment
Verify jobs are running
check agent status
Check the gateway status
Check the Agents are in the CCM
| Start | Finish
Post Upgrade tasks
Backup the new Control-M/server environment
Upgrade Complete

## EM 9.0.18-19-20 upgrade plan
Enterprise Manager 9.0.18/9.0.19/9.0.20 Sample Upgrade Plan
Actions prior to the upgrade | Start | Finish
Validate that the source EM 9.0.x has the latest fix pack installed.
Review the 9.0.18/9.0.19/9.0.20 Upgrade Requirements and Considerations
9.0.18 - http://documents.bmc.com/supportu/9.0.18/help/Main_help/en-US/index.htm#94278.htm
9.0.19 - http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#94278.htm
9.0.20 - http://documents.bmc.com/supportu/9.0.20/help/Main_help/en-US/index.htm#94278.htm
On the "old" Control-M/Enterprise Manager database run the query below. If it throw results, you have duplicated folders in the EM database that could represent an issue for the upgrade, contact BMC Support to delete the duplicated entries. select DATA_CENTER, SCHED_TABLE, DSN, TABLE_STATUS, TBL_DELETION_TIMESTAMP, count(*) from DEF_VER_TABLES group by DATA_CENTER, SCHED_TABLE, DSN, TABLE_STATUS, TBL_DELETION_TIMESTAMP having count(*)>1; For 9.0.20 this step is not necessary. If you are upgrading from a version earlier than 9.0.19, the installation checks and verifies that there are no duplicate scheduling folder names in database. If any exist, the installation exits with an error message and provide the steps to solve it.
Perform the steps described in the "Control-M Reporting Facility migration" section of the Migration guide to migrate reports from the old Control-M Reporting Facility to the new Control-M Reports. The next video describes the procedure:
https://youtu.be/gnWfoDlnk7U
http://documents.bmc.com/supportu/9.0.18/help/Main_help/en-US/index.htm#94198.htm
Finalize upgrade details | Start | Finish
Select the cutover date
Determine the outage window.
For Distributed architectures (more than one EM server) you must consider the upgrade of all the EM servers on the same outage window.
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover | Start | Finish
Perform any needed backups of the 9.0.x environment
Copy the DROST.9.0.18/9.0.19/9.0.20 file to the 9.0.x environment
Validate that you have at least 10 GB available in the EM 9.0.x file system
EM cutover | Start | Finish
Verify all scheduling tables are in sync between EM and Control-M/Server.
Run the setup.exe (Windows) or setup.sh (UNIX/LINUX) to perform the upgrade. If you have enabled High Availability for EM, please follow the next steps: a. Stop the Control-M/Enterprise Manager Configuration Agent on the secondary node. b. Using CCM, shutdown the EM components in the primary server: GCS, GUI Server, GAS, gateways and any other EM components, stop the Control-M/Enterprise Manager Configuration Agent. c. Upgrade primary EM server. d. Upgrade secondary EM server. e. Start primary EM f. Start the configuration agent on the secondary EM.
Using CCM, connect to CMS and verify the hostname, ports and definitions for the new environment.
Verify the new environment | Start | Finish
Verify components and gateways are running
Start EM GUI client, verify jobs.
Order new test table/jobs
View job definitions in the EM GUI
Verify different viewpoints
Verify all resources have been refreshed and new ones are being added/deleted properly
Access sysout and log files for a job
Perform normal AJF actions: hold, update, free, …
Verify security: view or add a user
Post Upgrade tasks | Start | Finish
Backup the new EM 9.0.18/9.0.19/9.0.20 environment
Upgrade Complete
Disable "Compatibility mode" when all your clients have been upgraded to 9.0.18/9.0.19/9.0.20

## Server9.0.18-19-20 upgrade plan
Control-M/Server 9.0.18/9.0.19/9.0.20 Sample Upgrade Plan
Actions prior to the upgrade | Start | Finish
Validate that the Control-M/Server 9.0.x has the latest fix pack installed.
Review the 9.0.18/9.0.19/9.0.20 Upgrade Requirements and Considerations
9.0.18 - http://documents.bmc.com/supportu/9.0.18/help/Main_help/en-US/index.htm#94278.htm
9.0.19 - http://documents.bmc.com/supportu/9.0.19/help/Main_help/en-US/index.htm#94278.htm
9.0.20 - http://documents.bmc.com/supportu/9.0.20/help/Main_help/en-US/index.htm#94278.htm
Finalize upgrade details | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover | Start | Finish
Perform any needed backups of the 9.0.x environment
Copy the DROST.9.0.18/9.0.19/9.0.20 file to the 9.0.x environment
Validate that you have at least 10 GB available in the Control-M/Server 9.0.x file system *Space required for the validation.
Run "ctmsetown -action list", does the output show any entry with the NOIMPL string? If so, contact BMC Support to solve this issue. Here's an example: &ctmagent@FIELD &bh3jbolpv05@FIELD &P@FIELD &NOTIMPL@LINE
Control-M/Server cutover | Start | Finish
Run the setup.exe (Windows) or setup.sh (UNIX/LINUX) to perform the upgrade. If you have enabled High Availability for Control-M/Server, please follow the next steps: a. Stop Control-M/Server Configuration Agent on the secondary node. b. Stop Control-M/Server and Control-M/Server Configuration Agent on the primary node. c. Upgrade primary Control-M/Server. d. Upgrade secondary Control-M/Server. e. Start Control-M/Server and Control-M/Server Configuration Agent on the primary node. f. Start Control-M/Server Configuration Agent on the secondary node.
Verify the new environment | Start | Finish
Verify jobs are running
check agent status
Check the gateway status
Check the Agents are in the CCM
Post Upgrade tasks | Start | Finish
Backup the new Control-M/server environment
Upgrade Complete
Disable "Compatibility mode" when all your clients have been upgraded to 9.0.18/9.0.19/9.0.20

## EM 9 sample upgrade plan
Enterprise Manager 9 Sample Upgrade Plan
New Software Installation |  | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts. Please check the "Control-M limits on UNIX accounts" section in the Installation Guide
Validate that the new server has the same time configuration than the source server
Install EM 9 and the latest EM fixpack
Install the EM 9 client and latest fixpack
Install the EM 9 Upgrade Export Pack in the "old" EM environment
Review the EM 9 Upgrade Considerations(000099896) | https://selfservice.bmc.com/casemgmt/sc_KnowledgeArticle?sfdcid=kA214000000d9IICAY&type=Solution
Testing |  | Start | Finish
On the "old" environment, run the Upgrade Export “Validation” report until there are no errors.
Export the "old" environment. You do not have to shutdown EM to perform this export.
Copy the export file to the new environment
Import the data into the new EM
Review the functionality of the EM 9 Workload Automation client. Review the Release Notes
Validate the functionality of the new EM client and Server
Test the new Client Distribution tool delivered with Control-M 9
Create a checklist of actions to verify the new installation after import(change a job, hold/free a job, re-run, view sysout, …)
Finalize upgrade details |  | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover |  | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new EM 9 components are not running(gateway, GUI Server, GCS, CMS, CORBA naming service)
Verfiy new EM 9 database is running
EM cutover |  | Start | Finish
Verify all scheduling tables are in sync between EM and Control-M/Server.
Using CCM, shutdown the EM components in the old environment: GCS, GUI Server, GAS, gateways and any other EM components.
Shutdown the EM Configuration Agent, EM Configuration Management Server and the Naming Service.
Make sure the EM database is up.
Run the Upgrade Export utility to export the old environment
Copy the file created by the upgrade export to the new EM 9
Using CCM, shutdown the EM components in the new environment: GCS, GUI Server, GAS, gateways and any other EM components. If you are using Control-M/Enterprise Manager 9.0 with High Availability, please follow the next steps before performing the import: 1. Stop the Control-M/Enterprise Manager Configuration Agent on the secondary node. 2. Using CCM, shutdown the EM components in the primary server: GCS, GUI Server, GAS, gateways and any other EM components, stop the Control-M/Enterprise Manager Configuration Agent.
Run Upgrade Toolkit Import utility to import data into the new EM 9
Using the “root_menu” in Unix go to Activation Menu > Start all, On Windows go to services.msc in Windows, start the Control-M/Enterprise Manager configuration agent. If you are using Control-M/Enterprise Manager 9.0 with High Availability, on the secondary EM, start the Control-M/Enterprise Manager Configuration Agent using "root_menu" for Unix and services.msc for Windows.
If the Control-M/Server is also being upgraded, perform "Elevate" for each Control-M/Server being upgraded before bringing up the gateway. During Elevate: Change the Host name from the OLD host to the NEW host name. If the elevate option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Using CCM, connect to CMS and verify the hostname, ports and definitions for the new environment.
If a distributed/secondary Control-M/Enterprise Manager 9.0 disappeared from Control-M Configuration Manager after performing the upgrade's import, please check the next article to solve it:
https://bmcsites.force.com/casemgmt/sc_KnowledgeArticle?sfdcid=000144902
Verify the new environment |  | Start | Finish
Verify components and gateways are running
Start EM GUI client, verify jobs.
Order new test table/jobs
View job definitions in the EM GUI
Verify different viewpoints
Verify all resources have been refreshed and new ones are being added/deleted properly
Access sysout and log files for a job
Perform normal AJF actions: hold, update, free, …
Verify security: view or add a user
Post Upgrade tasks |  | Start | Finish
Backup the new EM environment
Upgrade Complete

## Server 9 sample upgrade plan
Control-M/Server 9 Sample Upgrade Plan
New Software Installation | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts. Please check the "Control-M limits on UNIX accounts" section in the Installation Guide
Validate that the new server has the same time configuration and Control-M log retention than the source server
Install Control-M/Server 9 and the latest fixpack
Install the Control-M/Server 9 Export utility in the "old" server environment
Testing | Start | Finish
On the "old" environment, run the Control-M/Server Upgrade Export Toolkit “Validation” report until there are no errors.
Export the "old" environment. You do not have to shutdown the Control-M/Server to perform this export.
Copy the export file to the new environment
Import the data into the new Control-M/Server
Review the functionality of the Control-M/Server Release Notes
Validate the functionality of the new Control-M/Server
Test the new agent deployment utility
Review the config.dat from the old environment and add any customization to the new environment
If database is Oracle, ensure the config.dat "LANGUAGE_TYPE" setting is set correctly as the Control-M/Server database owner system variable NLS_LANG
Validate the SMTP server setting
Create a checklist of actions to verify the new installation after import(send a shout, send an email, …)
Copy customized scripts from the old to new environment
Finalize upgrade details | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new Control-M/Server 9 database is running
Control-M/Server cutover | Start | Finish
Shutdown the old Control-M/Server configuration agent and Control-M/Server. Leave the database up and running. If you are using the upgrade toolkit’s functionality to add the new Control-M/Server’s host name to the agents, you need to keep the Control-M/Server up for the first part of the export and shut it down once the new host name has been added to complete the export of the active environment.
Run the Upgrade Export utility to export the old environment
Copy the file created by the upgrade export to the new Control-M/Server V9
Run Upgrade Toolkit Import utility to import data into the new Control-M/Server V9. If you have Control-M/Server 9.0 with High Availability and Postgres, please follow the next steps before performing the import: 1. Change the replication mode to asynchronous on the primary (active) Control-M/Server: ctmha -ACTION UPDATE_REPLICATION_MODE ASYNC 2. Stop the Control-M/Server Configuration Agent on the secondary node. 3. Stop the Control-M/Server Configuration Agent and Control-M/Server on the primary node.
Run ‘ctmdbcount’ on the source and target environment, compare both outputs to validate that all the tables have been imported.
Run 'ctmdbopt' to improve database performance
Validate that all the historical and statistics have been imported successfully.
Check Control-M/Server default protocol_version and server to agent port
Before starting the Control-M/Server, from the CCM, right-click this Control-M/Server and run Promote datacenter. If the promote option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Start the Control-M/Server and Control-M/Server configuration agent. If you have Control-M/Server 9.0 with High Availability and Postgres, please follow the next steps: 1. Start the Control-M/Server Configuration Agent and Control-M/Server on the primary node. 2. Start the Control-M/Server Configuration Agent on the secondary node. 3. On the Control-M Configuration Manager validate that High Availability is working correctly. 4. Change the replication mode back to synchronous by running the next command on the primary (active) Control-M/Server: ctmha -ACTION UPDATE_REPLICATION_MODE SYNC
Verify the new environment | Start | Finish
Verify jobs are running
check agent status
Check the gateway status
Check the Agents are in the CCM
Post Upgrade tasks | Start | Finish
Backup the new Control-M/server environment
Upgrade Complete

## EM V8 sample upgrade plan (hidden)
Enterprise Manager V8 Sample Upgrade Plan
New Software Installation |  | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts. Please check the "Control-M limits on UNIX accounts" section in the Installation Guide
Validate that the new server has the same time configuration than the source server
Install EM V8 and the latest EM fixpack
Install the EM V8 client and latest fixpack
Install the EM V8 Export utility in the "old" EM environment
Review the EM V8 Upgrade Considerations(000095659) | https://selfservice.bmc.com/casemgmt/sc_KnowledgeArticle?sfdcid=kA214000000d86PCAQ&type=Solution
Testing |  | Start | Finish
On the "old" environment, run the Upgrade Export Toolkit “Validation” report until there are no errors.
Export the "old" environment. You do not have to shutdown EM to perform this export.
Copy the export file to the new environment
Import the data into the new EM
Review the functionality of the EM V8 Workload Automation client. Review the Release Notes
Validate the functionality of the new EM client and Server
Create a checklist of actions to verify the new installation after import(change a job, hold/free a job, re-run, view sysout, …)
Finalize upgrade details |  | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover |  | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new EM V8 components are not running(gateway, GUI Server, GCS, CMS, CORBA naming service)
Verfiy new EM V8 database is running
EM cutover |  | Start | Finish
Verify all scheduling tables are in sync between EM and Control-M/Server.
Using CCM, shutdown the EM components in the old environment: GCS, GUI Server, GAS, gateways and any other EM components.
Shutdown the EM Configuration Agent, EM Configuration Management Server and the Naming Service.
Make sure the EM database is up.
Run the Upgrade Export utility to export the old environment
Copy the file created by the upgrade export to the new EM V8
Using CCM, shutdown the EM components in the new environment: GCS, GUI Server, GAS, gateways and any other EM components.
Run Upgrade Toolkit Import utility to import data into the new EM V8
Using the “root_menu” in Unix or services.msc in Windows, start the Naming service
Using the “root_menu” in Unix or services.msc in Windows, start CMS – Configuration Management System.
If the Control-M/Server is also being upgraded, perform "Promote" for each Control-M/Server being upgraded before bringing up the gateway. During Promote: Change the Host name from the OLD host to the NEW host name. If the promote option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Using CCM, connect to CMS and verify the hostname, ports and definitions for the new environment.
Verify the new environment |  | Start | Finish
Verify components and gateways are running
Start EM GUI client, verify jobs.
Order new test table/jobs
View job definitions in the EM GUI
Verify different viewpoints
Verify all resources have been refreshed and new ones are being added/deleted properly
Access sysout and log files for a job
Perform normal AJF actions: hold, update, free, …
Verify security: view or add a user
Post Upgrade tasks |  | Start | Finish
Backup the new EM environment
Upgrade Complete

## Server V8 sample upgrade plan (hidden)
Control-M/Server V8 Sample Upgrade Plan
New Software Installation |  | Start | Finish
If you are installing on a UNIX/Linux server, please validate that the right limits for the Control-M accounts. Please check the "Control-M limits on UNIX accounts" section in the Installation Guide
Validate that the new server has the same time configuration and Control-M log retention than the source server
Install Control-M/Server V8 and the latest fixpack
Install the Control-M/Server V8 Export utility in the "old" server environment
Review the Control-M/Server Upgrade considerations(000095837) | https://selfservice.bmc.com/casemgmt/sc_KnowledgeArticle?sfdcid=kA214000000d89HCAQ&type=Solution
Testing |  | Start | Finish
On the "old" environment, run the Control-M/Server Upgrade Export Toolkit “Validation” report until there are no errors.
Export the "old" environment. You do not have to shutdown the Control-M/Server to perform this export.
Copy the export file to the new environment
Import the data into the new Control-M/Server
Review the functionality of the Control-M/Server Release Notes
Validate the functionality of the new Control-M/Server
Review the config.dat from the old environment and add any customization to the new environment
If database is Oracle, ensure the config.dat "LANGUAGE_TYPE" setting is set correctly as the Control-M/Server database owner system variable NLS_LANG
Validate the SMTP server setting
Create a checklist of actions to verify the new installation after import(send a shout, send an email, …)
Copy customized scripts from the old to new environment
Finalize upgrade details |  | Start | Finish
Select the cutover date
Determine the outage window
Create the back-out plan
at least 2 weeks before the cutover date, open and AMIGO Review issue with BMC Support and include the upgrade plan
Actions prior to the cutover |  | Start | Finish
Ensure you have the DBA password and DBO name and password prior to the migration export/import
Re-run the export validation report on the old environment
Perform any needed backups of the old environment
Verfiy new Control-M/Server V8 database is running
Control-M/Server cutover |  | Start | Finish
Shutdown the old Control-M/Server configuration agent and Control-M/Server. Leave the database up and running. If you are using the upgrade toolkit’s functionality to add the new Control-M/Server’s host name to the agents, you need to keep the Control-M/Server up for the first part of the export and shut it down once the new host name has been added to complete the export of the active environment.
Run the Upgrade Export utility to export the old environment
Copy the file created by the upgrade export to the new Control-M/Server V8
Run Upgrade Toolkit Import utility to import data into the new Control-M/Server V8
Run ‘ctmdbcount’ on the source and target environment, compare both outputs to validate that all the tables have been imported.
Run 'ctmdbopt' to improve database performance
Validate that all the historical and statistics have been imported successfully.
Check Control-M/Server default protocol_version and server to agent port
Before starting the Control-M/Server, from the CCM, right-click this Control-M/Server and run Promote datacenter. If the promote option is greyed out, please do right click over the Control-M/Server, set to unmanaged and try again.
Start the Control-M/Server
Start the Control-M/Server configuration agent
Verify the new environment |  | Start | Finish
Verify jobs are running
check agent status
Check the gateway status
Check the Agents are in the CCM
Post Upgrade tasks |  | Start | Finish
Backup the new Control-M/server environment
Upgrade Complete